# DEME V3 Sprint Plan: Multi-Agent Ethics with Rank 4-6 Tensors

Version: 2.0 Date: January 2026 Total Sprints: 28 (2-week sprints) Estimated Duration: 56 weeks

## Sprint Overview

| Phase | Sprints | Focus Area | Key Deliverables |
| --- | --- | --- | --- |
| Phase 1 | 1-3 | Foundation | MoralTensor core, V2 compatibility |
| Phase 2 | 4-6 | Rank-2 Distributional | Per-party ethics, fairness metrics |
| Phase 3 | 7-10 | Rank-3/4 Multi-Agent | Temporal, coalitions, Shapley |
| Phase 4 | 11-13 | Hardware Acceleration | CUDA, Jetson Nano, TensorRT |
| Phase 5 | 14-16 | Rank-5/6 Advanced | Uncertainty, full context |
| Phase 6 | 17-18 | Production Hardening | Testing, docs, migration tools |
| Phase 7 | 19-21 | Decentralized Infrastructure | DHT, E-Certs, Blockchain ledger |
| Phase 8 | 22-24 | Enforcement & Auditing | EA, Conflict Resolution, SAIDS |
| Phase 9 | 25-26 | TCAM & Performance | Hardware veto acceleration |
| Phase 10 | 27-28 | Stakeholder Tooling | Drift detection, formal verification |

## Phase 1: Foundation (Sprints 1-3)

### Sprint 1: MoralTensor Core Data Structure

Goal: Implement the fundamental MoralTensor class supporting ranks 1-6

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 1.1 | Design MoralTensor dataclass with rank-aware shape validation | P0 | 8 |
| 1.2 | Implement dense tensor storage with NumPy backend | P0 | 6 |
| 1.3 | Implement sparse tensor storage (COO format) | P0 | 8 |
| 1.4 | Add dimension naming and metadata tracking | P1 | 4 |
| 1.5 | Implement __repr__, __eq__, serialization | P1 | 4 |
| 1.6 | Add veto_flags and veto_locations for tensor elements | P0 | 6 |
| 1.7 | Write comprehensive unit tests for MoralTensor | P0 | 8 |
| 1.8 | Create type stubs and documentation | P1 | 4 |

Deliverables: - src/erisml/ethics/moral_tensor.py - tests/test_moral_tensor.py - API documentation for MoralTensor

Dependencies: None

Acceptance Criteria: - [ ] MoralTensor supports ranks 1-6 with shape validation - [ ] Sparse and dense representations interconvertible - [ ] 95% test coverage on core class - [ ] Serialization round-trip works

### Sprint 2: Tensor Operations Library

Goal: Implement core tensor operations needed for ethics computation

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 2.1 | Implement contract() for weighted axis reduction | P0 | 8 |
| 2.2 | Implement slice_party(), slice_time() accessors | P0 | 6 |
| 2.3 | Implement element-wise operations (__add__, __mul__, etc.) | P0 | 6 |
| 2.4 | Implement to_vector() collapse with strategies | P0 | 8 |
| 2.5 | Implement promote_rank() for dimension expansion | P1 | 6 |
| 2.6 | Implement distance metrics (Euclidean, Wasserstein) | P1 | 8 |
| 2.7 | Implement dominates() for Pareto comparison | P0 | 6 |
| 2.8 | Performance benchmarks for all operations | P1 | 4 |
| 2.9 | Unit tests for all operations | P0 | 8 |

Deliverables: - Extended moral_tensor.py with operations - src/erisml/ethics/tensor_ops.py (helper functions) - tests/test_tensor_ops.py - Benchmark results document

Dependencies: Sprint 1

Acceptance Criteria: - [ ] All operations work for ranks 1-6 - [ ] Sparse operations maintain sparsity where possible - [ ] Rank-2 contraction < 200ns (CPU) - [ ] 90% test coverage

### Sprint 3: V2 Compatibility Layer

Goal: Ensure seamless interoperability between V2 MoralVector and V3 MoralTensor

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 3.1 | Implement promote_v2_to_v3() conversion function | P0 | 6 |
| 3.2 | Implement collapse_v3_to_v2() with multiple strategies | P0 | 8 |
| 3.3 | Update MoralVector to inherit from/wrap MoralTensor(rank=1) | P0 | 8 |
| 3.4 | Ensure MoralLandscape works with mixed Vector/Tensor inputs | P1 | 6 |
| 3.5 | Add deprecation warnings for pure V2 usage | P2 | 2 |
| 3.6 | Write V2 ↔ V3 round-trip invariance tests | P0 | 8 |
| 3.7 | Update existing V2 tests to verify V3 compatibility | P0 | 6 |
| 3.8 | Migration guide documentation | P1 | 4 |

Deliverables: - src/erisml/ethics/compat.py - Updated moral_vector.py with V3 integration - tests/test_v2_v3_compat.py - Migration guide document

Dependencies: Sprints 1-2

Acceptance Criteria: - [ ] All existing V2 tests pass unchanged - [ ] V2 → V3 → V2 round-trip preserves values - [ ] No breaking API changes for V2 consumers - [ ] Performance within 10% of V2 baseline

## Phase 2: Rank-2 Distributional Ethics (Sprints 4-6)

### Sprint 4: EthicalFactsV3 with Per-Party Tracking

Goal: Extend EthicalFacts to track impacts on individual parties

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 4.1 | Design ConsequencesV3 with per-party distributions | P0 | 6 |
| 4.2 | Design RightsAndDutiesV3 with per-party tracking | P0 | 6 |
| 4.3 | Design JusticeAndFairnessV3 with distributional metrics | P0 | 6 |
| 4.4 | Implement EthicalFactsV3 dataclass | P0 | 8 |
| 4.5 | Implement V2 → V3 facts promotion (single party default) | P0 | 4 |
| 4.6 | Implement V3 → V2 facts collapse | P1 | 4 |
| 4.7 | Update JSON schema for V3 facts | P1 | 6 |
| 4.8 | Write unit tests | P0 | 6 |
| 4.9 | Update domain interface protocols | P1 | 4 |

Deliverables: - src/erisml/ethics/facts_v3.py - Updated schemas/ethical_facts_v3.json - tests/test_facts_v3.py

Dependencies: Sprint 3

Acceptance Criteria: - [ ] EthicalFactsV3 supports 1-N parties - [ ] V2 facts auto-promote to V3 - [ ] JSON serialization complete - [ ] Type validation enforced

### Sprint 5: Distributional Fairness Metrics

Goal: Implement fairness and distributional justice metrics on tensors

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 5.1 | Implement Gini coefficient for harm/benefit distribution | P0 | 6 |
| 5.2 | Implement Rawlsian maximin (worst-off identification) | P0 | 6 |
| 5.3 | Implement utilitarian aggregation (sum/average) | P0 | 4 |
| 5.4 | Implement prioritarian weighting (vulnerability-adjusted) | P0 | 6 |
| 5.5 | Implement Atkinson inequality index | P1 | 6 |
| 5.6 | Implement Theil index for multi-dimension inequality | P1 | 6 |
| 5.7 | Create FairnessMetrics class aggregating all metrics | P0 | 6 |
| 5.8 | Unit tests with edge cases | P0 | 8 |
| 5.9 | Documentation with examples | P1 | 4 |

Deliverables: - src/erisml/ethics/fairness_metrics.py - tests/test_fairness_metrics.py - Fairness metrics documentation

Dependencies: Sprint 4

Acceptance Criteria: - [ ] All metrics implemented and tested - [ ] Edge cases handled (empty, single party) - [ ] Numerical stability verified - [ ] Documentation with usage examples

### Sprint 6: EthicsModuleV3 and JudgementV3

Goal: Define V3 EM protocol and judgement format with tensor output

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 6.1 | Design EthicsModuleV3 protocol with tensor output | P0 | 6 |
| 6.2 | Design EthicalJudgementV3 dataclass | P0 | 6 |
| 6.3 | Implement BaseEthicsModuleV3 with template methods | P0 | 8 |
| 6.4 | Implement judge_distributed() method | P0 | 6 |
| 6.5 | Update GenevaEMV2 → GenevaEMV3 | P1 | 6 |
| 6.6 | Update CaseStudy1TriageEM → TriageEMV3 | P1 | 6 |
| 6.7 | Implement judgement V2 ↔ V3 conversion | P0 | 4 |
| 6.8 | Unit tests for V3 EMs | P0 | 8 |

Deliverables: - src/erisml/ethics/modules/base_v3.py - src/erisml/ethics/judgement_v3.py - Updated example EMs - tests/test_em_v3.py

Dependencies: Sprints 4-5

Acceptance Criteria: - [ ] V3 protocol defined and documented - [ ] At least 2 reference V3 EMs implemented - [ ] V2 EMs still work via compatibility layer - [ ] Judgement conversion round-trips correctly

## Phase 3: Rank-3/4 Multi-Agent Ethics (Sprints 7-10)

### Sprint 7: Temporal Tensor Support (Rank-3)

Goal: Enable time-evolving ethical assessment

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 7.1 | Extend MoralTensor with temporal axis support | P0 | 6 |
| 7.2 | Implement time_steps metadata and duration tracking | P0 | 4 |
| 7.3 | Implement temporal discounting operations | P0 | 6 |
| 7.4 | Implement irreversibility detection across time | P0 | 8 |
| 7.5 | Implement trajectory comparison (DTW distance) | P1 | 8 |
| 7.6 | Update EthicalFactsV3 with harm/benefit trajectories | P0 | 6 |
| 7.7 | Implement slice_time() and window() operations | P0 | 6 |
| 7.8 | Unit tests for temporal operations | P0 | 8 |

Deliverables: - Extended moral_tensor.py with temporal support - src/erisml/ethics/temporal_ops.py - tests/test_temporal_tensor.py

Dependencies: Sprint 6

Acceptance Criteria: - [ ] Rank-3 tensors work end-to-end - [ ] Discounting configurable per-party - [ ] Irreversibility veto triggers appropriately - [ ] Trajectory distance metrics implemented

### Sprint 8: Coalition Context (Rank-4 Foundation)

Goal: Support multi-agent action coordination in tensors

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 8.1 | Design CoalitionContext dataclass | P0 | 6 |
| 8.2 | Extend MoralTensor with action and coalition axes | P0 | 8 |
| 8.3 | Implement coalition configuration enumeration | P0 | 6 |
| 8.4 | Implement sparse coalition representation | P0 | 8 |
| 8.5 | Add coalition stability constraints | P1 | 6 |
| 8.6 | Update EthicalFactsV3 with coalition context | P0 | 4 |
| 8.7 | Implement action-conditioned slicing | P0 | 6 |
| 8.8 | Unit tests for rank-4 tensors | P0 | 8 |

Deliverables: - src/erisml/ethics/coalition.py - Extended tensor support - tests/test_coalition_tensor.py

Dependencies: Sprint 7

Acceptance Criteria: - [ ] Rank-4 tensors functional - [ ] Sparse representation efficient for large coalition spaces - [ ] Coalition enumeration correct - [ ] Action-conditioned operations work

### Sprint 9: Shapley Values and Fair Credit Assignment

Goal: Implement game-theoretic fair attribution for multi-agent ethics

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 9.1 | Implement exact Shapley value computation | P0 | 10 |
| 9.2 | Implement Monte Carlo Shapley approximation | P0 | 8 |
| 9.3 | Implement contribution margin per agent | P0 | 6 |
| 9.4 | Implement core stability check | P1 | 8 |
| 9.5 | Implement nucleolus computation | P2 | 8 |
| 9.6 | Add Shapley to EthicalJudgementV3 metadata | P1 | 4 |
| 9.7 | Benchmark exact vs approximate for various sizes | P1 | 4 |
| 9.8 | Unit tests with known game theory examples | P0 | 8 |

Deliverables: - src/erisml/ethics/game_theory.py - Shapley integration in judgements - tests/test_shapley.py - Performance analysis document

Dependencies: Sprint 8

Acceptance Criteria: - [ ] Exact Shapley correct for n ≤ 10 agents - [ ] Monte Carlo within 5% for n ≤ 100 - [ ] Core stability detection works - [ ] Integration with decision proofs

### Sprint 10: Strategic Layer Implementation

Goal: Complete the Strategic layer of the three-layer pipeline

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 10.1 | Design StrategicLayer interface | P0 | 6 |
| 10.2 | Implement coalition stability analysis | P0 | 8 |
| 10.3 | Implement Nash equilibrium detection | P1 | 10 |
| 10.4 | Implement policy recommendation generation | P1 | 8 |
| 10.5 | Integrate strategic layer into DEMEPipeline | P0 | 6 |
| 10.6 | Add strategic layer to decision proofs | P0 | 6 |
| 10.7 | End-to-end integration tests | P0 | 8 |
| 10.8 | Documentation and examples | P1 | 4 |

Deliverables: - src/erisml/ethics/layers/strategic.py (completed) - Updated pipeline.py - tests/test_strategic_layer.py - Multi-agent example scenario

Dependencies: Sprint 9

Acceptance Criteria: - [ ] Strategic layer functional - [ ] Pipeline executes all three layers - [ ] Decision proofs include strategic analysis - [ ] Example demonstrates full multi-agent decision

## Phase 4: Hardware Acceleration (Sprints 11-13)

### Sprint 11: Acceleration Framework and CPU Optimization

Goal: Build acceleration abstraction layer with optimized CPU backend

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 11.1 | Design AccelerationBackend abstract interface | P0 | 6 |
| 11.2 | Implement CPUBackend with NumPy/SciPy | P0 | 8 |
| 11.3 | Implement SIMD-optimized tensor operations | P1 | 10 |
| 11.4 | Implement sparse tensor optimization (SciPy) | P0 | 8 |
| 11.5 | Create AccelerationDispatcher for backend selection | P0 | 6 |
| 11.6 | Add device hints to MoralTensor | P1 | 4 |
| 11.7 | Benchmark suite for acceleration backends | P0 | 6 |
| 11.8 | Unit tests for dispatcher and CPU backend | P0 | 6 |

Deliverables: - src/erisml/ethics/acceleration/__init__.py - src/erisml/ethics/acceleration/backend.py - src/erisml/ethics/acceleration/cpu.py - tests/test_acceleration.py - Benchmark results

Dependencies: Sprint 10

Acceptance Criteria: - [ ] Backend abstraction clean and extensible - [ ] CPU backend ≥ baseline NumPy performance - [ ] Sparse operations 10x faster for sparse tensors - [ ] Dispatcher correctly selects backend

### Sprint 12: CUDA Backend

Goal: Implement GPU acceleration for tensor operations

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 12.1 | Implement CUDABackend using CuPy | P0 | 10 |
| 12.2 | Implement GPU memory management | P0 | 8 |
| 12.3 | Implement async data transfer (pinned memory) | P1 | 6 |
| 12.4 | Optimize contraction kernels | P1 | 8 |
| 12.5 | Implement batched operations | P0 | 6 |
| 12.6 | Add CUDA stream support for pipelining | P2 | 6 |
| 12.7 | Benchmark CPU vs CUDA across tensor sizes | P0 | 4 |
| 12.8 | Fallback handling when CUDA unavailable | P0 | 4 |
| 12.9 | Unit tests (requires CUDA hardware) | P0 | 6 |

Deliverables: - src/erisml/ethics/acceleration/cuda.py - Updated dispatcher with CUDA support - tests/test_cuda_backend.py - CUDA vs CPU benchmark report

Dependencies: Sprint 11

Acceptance Criteria: - [ ] CUDA backend functional on NVIDIA GPUs - [ ] 10x+ speedup for rank-4+ tensors - [ ] Graceful fallback on non-CUDA systems - [ ] Memory usage reasonable

### Sprint 13: Jetson Nano Integration

Goal: Enable edge deployment on NVIDIA Jetson Nano with optimizations

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 13.1 | Implement JetsonBackend with device detection | P0 | 8 |
| 13.2 | Implement TensorRT optimization for tensor ops | P0 | 12 |
| 13.3 | Implement DLA support for Orin devices | P1 | 8 |
| 13.4 | Add power mode configuration | P1 | 4 |
| 13.5 | Implement unified memory optimization | P0 | 6 |
| 13.6 | Create pre-compiled TensorRT engine caching | P1 | 6 |
| 13.7 | Implement EPU placeholder for future devices | P2 | 4 |
| 13.8 | Benchmark on Jetson Nano 4GB | P0 | 6 |
| 13.9 | Benchmark on Jetson Orin (if available) | P1 | 4 |
| 13.10 | Integration tests on Jetson hardware | P0 | 6 |

Deliverables: - src/erisml/ethics/acceleration/jetson.py - src/erisml/ethics/acceleration/tensorrt_utils.py - JetsonConfig dataclass - Jetson deployment guide - Benchmark results

Dependencies: Sprint 12

Acceptance Criteria: - [ ] Jetson Nano 4GB fully supported - [ ] TensorRT provides 3x+ speedup over CPU - [ ] DLA works on Orin (if hardware available) - [ ] Power modes configurable - [ ] Engine caching reduces startup time

## Phase 5: Rank-5/6 Advanced Features (Sprints 14-16)

### Sprint 14: Uncertainty Quantification (Rank-5)

Goal: Enable Monte Carlo uncertainty propagation in ethics

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 14.1 | Extend MoralTensor with sample axis | P0 | 6 |
| 14.2 | Implement sample generation from distributions | P0 | 8 |
| 14.3 | Implement expected value and variance computation | P0 | 6 |
| 14.4 | Implement Conditional Value at Risk (CVaR) | P0 | 8 |
| 14.5 | Implement worst-case (robust) aggregation | P0 | 6 |
| 14.6 | Implement confidence interval computation | P1 | 6 |
| 14.7 | Update EthicalFactsV3 with uncertainty bounds | P0 | 6 |
| 14.8 | Unit tests for uncertainty propagation | P0 | 8 |

Deliverables: - src/erisml/ethics/uncertainty.py - Extended tensor support - tests/test_uncertainty.py

Dependencies: Sprint 13

Acceptance Criteria: - [ ] Rank-5 tensors functional - [ ] Monte Carlo sampling efficient - [ ] CVaR and robust methods implemented - [ ] Confidence intervals correct

### Sprint 15: Full Context Tensors (Rank-6)

Goal: Support complete ethical state space representation

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 15.1 | Implement rank-6 tensor support | P0 | 8 |
| 15.2 | Implement Tucker decomposition for compression | P0 | 10 |
| 15.3 | Implement Tensor Train decomposition | P1 | 10 |
| 15.4 | Implement hierarchical sparse storage | P0 | 8 |
| 15.5 | Optimize memory layout for access patterns | P1 | 6 |
| 15.6 | Benchmark rank-6 operations | P0 | 6 |
| 15.7 | Integration with acceleration backends | P0 | 6 |
| 15.8 | Unit tests for rank-6 tensors | P0 | 8 |

Deliverables: - Full rank-6 tensor support - src/erisml/ethics/tensor_decomposition.py - tests/test_rank6_tensor.py - Memory optimization guide

Dependencies: Sprint 14

Acceptance Criteria: - [ ] Rank-6 tensors work end-to-end - [ ] Decomposition reduces memory >10x - [ ] Operations on decomposed tensors efficient - [ ] All acceleration backends support rank-6

### Sprint 16: Advanced Decision Proofs

Goal: Extend audit trail for full tensor and multi-agent scenarios

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 16.1 | Extend DecisionProof for tensor hashing | P0 | 6 |
| 16.2 | Implement coalition stability certificates | P0 | 8 |
| 16.3 | Implement Shapley value audit records | P0 | 6 |
| 16.4 | Implement distributional fairness attestations | P0 | 6 |
| 16.5 | Implement temporal trajectory proofs | P1 | 6 |
| 16.6 | Implement uncertainty bound certificates | P1 | 6 |
| 16.7 | Update MCP server for V3 proofs | P1 | 6 |
| 16.8 | Unit tests for extended proofs | P0 | 8 |
| 16.9 | Documentation | P1 | 4 |

Deliverables: - Updated decision_proof.py → decision_proof_v3.py - Coalition certificates - Fairness attestations - tests/test_decision_proof_v3.py

Dependencies: Sprint 15

Acceptance Criteria: - [ ] All V3 features auditable - [ ] Proof verification works - [ ] MCP server exposes V3 proofs - [ ] Documentation complete

## Phase 6: Production Hardening (Sprints 17-18)

### Sprint 17: Comprehensive Testing and Bond Index

Goal: Achieve production-quality test coverage and representational coherence

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 17.1 | Extend Bond Index tests for tensor transforms | P0 | 10 |
| 17.2 | Add multi-agent invariance transforms | P0 | 8 |
| 17.3 | Full integration test suite | P0 | 10 |
| 17.4 | Hardware matrix testing (CPU/CUDA/Jetson) | P0 | 8 |
| 17.5 | Performance regression test suite | P0 | 6 |
| 17.6 | Fuzz testing for edge cases | P1 | 8 |
| 17.7 | Security audit of tensor operations | P1 | 6 |
| 17.8 | Coverage report and gap analysis | P0 | 4 |

Deliverables: - Extended Bond Index tests - Full integration test suite - Hardware test matrix - Coverage report (target: 90%+)

Dependencies: Sprint 16

Acceptance Criteria: - [ ] 90%+ code coverage - [ ] Bond Index < 0.1 for all V3 EMs - [ ] All hardware backends tested - [ ] No critical security issues

### Sprint 18: Documentation and Migration Tools

Goal: Enable production adoption with complete documentation and tooling

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 18.1 | Complete API documentation | P0 | 10 |
| 18.2 | Write V2 → V3 migration guide | P0 | 8 |
| 18.3 | Create migration CLI tool | P1 | 8 |
| 18.4 | Update README for V3 | P0 | 4 |
| 18.5 | Create V3 tutorial notebooks | P1 | 8 |
| 18.6 | Update JSON schemas to V05 | P0 | 4 |
| 18.7 | Release notes and changelog | P0 | 4 |
| 18.8 | Jetson deployment guide | P1 | 6 |
| 18.9 | Final review and cleanup | P0 | 8 |

Deliverables: - Complete API documentation - Migration guide - deme-migrate CLI tool - Updated README - Tutorial notebooks - V05 schemas - Release notes

Dependencies: Sprint 17

Acceptance Criteria: - [ ] All public APIs documented - [ ] Migration guide tested on real projects - [ ] CLI tool functional - [ ] Tutorials work end-to-end - [ ] Ready for release

## Phase 7: Decentralized Infrastructure (Sprints 19-21)

### Sprint 19: DHT Integration and Shadow Copies

Goal: Implement decentralized Ethics Module distribution

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 19.1 | Design DHT node architecture (Kademlia-based) | P0 | 10 |
| 19.2 | Implement KademliaNode class for EM indexing | P0 | 12 |
| 19.3 | Implement ShadowCopyManager for local EM caching | P0 | 8 |
| 19.4 | Design EM Service API for DHT queries | P0 | 6 |
| 19.5 | Implement offline capability with shadow copies | P1 | 8 |
| 19.6 | Add DHT health monitoring and replication | P1 | 6 |
| 19.7 | Unit tests for DHT operations | P0 | 8 |
| 19.8 | Integration tests for shadow copy sync | P0 | 6 |

Deliverables: - src/erisml/ethics/distribution/dht.py - src/erisml/ethics/distribution/shadow_cache.py - src/erisml/ethics/distribution/em_service.py - tests/test_dht_distribution.py

Dependencies: Sprint 18

Acceptance Criteria: - [ ] DHT node joins and leaves network correctly - [ ] Shadow copies sync with cryptographic verification - [ ] EM retrieval works offline from cache - [ ] API returns last verified EM version

### Sprint 20: E-Cert Schema and Governance CA

Goal: Establish cryptographic trust infrastructure

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 20.1 | Design ECertificate dataclass schema | P0 | 6 |
| 20.2 | Implement Governance CA key management | P0 | 10 |
| 20.3 | Implement E-Cert signing and verification | P0 | 8 |
| 20.4 | Design Certificate Revocation List (CRL) system | P0 | 8 |
| 20.5 | Implement secure EM loading protocol | P0 | 10 |
| 20.6 | Add Policy OID registry | P1 | 6 |
| 20.7 | Unit tests for cryptographic operations | P0 | 8 |
| 20.8 | Security audit of CA implementation | P0 | 8 |

Deliverables: - src/erisml/ethics/security/e_cert.py - src/erisml/ethics/security/governance_ca.py - src/erisml/ethics/security/secure_loader.py - tests/test_e_cert.py

Dependencies: Sprint 19

Acceptance Criteria: - [ ] E-Certs sign and verify correctly - [ ] CRL checks block revoked certificates - [ ] Secure loading sequence enforced - [ ] No security vulnerabilities in audit

### Sprint 21: Blockchain Ledger and Trustless Execution

Goal: Implement immutable audit trail and sandboxed execution

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 21.1 | Design blockchain ledger interface | P0 | 8 |
| 21.2 | Implement Stakeholder Consensus Event recording | P0 | 10 |
| 21.3 | Integrate with external blockchain (Ethereum/Polygon) | P1 | 12 |
| 21.4 | Research and select sandbox technology (WASM/SGX) | P0 | 8 |
| 21.5 | Implement sandboxed EM execution environment | P0 | 12 |
| 21.6 | Design trusted data oracle for EthicalFacts | P1 | 8 |
| 21.7 | Integration tests for full trust chain | P0 | 8 |
| 21.8 | Documentation for trust architecture | P1 | 4 |

Deliverables: - src/erisml/ethics/security/blockchain_ledger.py - src/erisml/ethics/security/sandbox.py - src/erisml/ethics/security/data_oracle.py - tests/test_blockchain_integration.py

Dependencies: Sprint 20

Acceptance Criteria: - [ ] EM approvals recorded on blockchain - [ ] Sandbox isolates untrusted EM code - [ ] Oracle validates off-chain EthicalFacts - [ ] Full trust chain verifiable end-to-end

## Phase 8: Enforcement & Auditing (Sprints 22-24)

### Sprint 22: Ethics Enforcement Agent

Goal: Implement dedicated agent for compliance monitoring

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 22.1 | Design EthicsEnforcementAgent architecture | P0 | 8 |
| 22.2 | Implement action monitoring against DecisionOutcome | P0 | 10 |
| 22.3 | Define InterventionType enum and protocols | P0 | 6 |
| 22.4 | Implement LOG, PAUSE, THROTTLE interventions | P0 | 10 |
| 22.5 | Implement action queue OVERRIDE | P1 | 8 |
| 22.6 | Add real-time audit trail integration | P0 | 8 |
| 22.7 | Unit tests for enforcement logic | P0 | 8 |
| 22.8 | Integration tests with governed agents | P0 | 8 |

Deliverables: - src/erisml/ethics/enforcement/agent.py - src/erisml/ethics/enforcement/intervention.py - src/erisml/ethics/enforcement/audit_integration.py - tests/test_enforcement_agent.py

Dependencies: Sprint 21

Acceptance Criteria: - [ ] EA detects action divergence from expected outcome - [ ] All intervention types functional - [ ] Every action cryptographically signed in audit - [ ] No false positives in compliance checks

### Sprint 23: Conflict Resolution and Metrics

Goal: Multi-agent conflict mediation and compliance dashboard

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 23.1 | Design ConflictResolutionModule | P0 | 8 |
| 23.2 | Implement conflict detection between agents | P0 | 10 |
| 23.3 | Implement mediation strategies (utilitarian, Rawlsian) | P0 | 10 |
| 23.4 | Design MetricsReportingAgent | P1 | 6 |
| 23.5 | Implement compliance rate tracking | P1 | 6 |
| 23.6 | Implement Hard Veto frequency metrics | P1 | 4 |
| 23.7 | Implement Epistemic Penalty averages | P1 | 4 |
| 23.8 | Build metrics dashboard API | P1 | 8 |
| 23.9 | Unit tests for conflict resolution | P0 | 8 |

Deliverables: - src/erisml/ethics/enforcement/conflict_resolution.py - src/erisml/ethics/enforcement/metrics.py - src/erisml/ethics/enforcement/dashboard.py - tests/test_conflict_resolution.py

Dependencies: Sprint 22

Acceptance Criteria: - [ ] Conflicts between agents detected and mediated - [ ] Metrics aggregated correctly - [ ] Dashboard API returns accurate statistics - [ ] Profile effectiveness trackable over time

### Sprint 24: SAIDS Agent and Internal Affairs

Goal: Self-auditing system to protect governance layer

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 24.1 | Design SAIDSAgent architecture | P0 | 8 |
| 24.2 | Implement Reward Firewall isolation | P0 | 10 |
| 24.3 | Implement behavioral drift detection model | P0 | 12 |
| 24.4 | Research and implement ZKP verification | P1 | 14 |
| 24.5 | Design Quarantine Protocol | P0 | 8 |
| 24.6 | Implement immediate EA isolation mechanism | P0 | 8 |
| 24.7 | Add Human-in-the-Loop notification | P1 | 6 |
| 24.8 | Security tests for SAIDS | P0 | 10 |

Deliverables: - src/erisml/ethics/enforcement/saids.py - src/erisml/ethics/enforcement/reward_firewall.py - src/erisml/ethics/enforcement/zkp_verifier.py - tests/test_saids.py

Dependencies: Sprint 23

Acceptance Criteria: - [ ] SAIDS monitors EA independently - [ ] Reward manipulation attempts blocked - [ ] Behavioral anomalies detected statistically - [ ] Quarantine isolates compromised EA immediately

## Phase 9: TCAM & Performance (Sprints 25-26)

### Sprint 25: TCAM Integration

Goal: Hardware-accelerated veto checking

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 25.1 | Research TCAM hardware options | P0 | 8 |
| 25.2 | Design TCAM ACL format for Hard Veto rules | P0 | 10 |
| 25.3 | Implement TCAM rule translator | P0 | 12 |
| 25.4 | Design hybrid pipeline (TCAM → Software) | P0 | 10 |
| 25.5 | Implement TCAM veto check integration | P0 | 10 |
| 25.6 | Add TCAM rule management tooling | P1 | 8 |
| 25.7 | Unit tests for rule translation | P0 | 6 |
| 25.8 | Integration tests for hybrid pipeline | P0 | 8 |

Deliverables: - src/erisml/ethics/acceleration/tcam.py - src/erisml/ethics/acceleration/tcam_translator.py - src/erisml/ethics/acceleration/hybrid_pipeline.py - tests/test_tcam.py

Dependencies: Sprint 24

Acceptance Criteria: - [ ] TCAM rules translate from software config - [ ] Hybrid pipeline checks TCAM before software - [ ] Nanosecond-level veto checks achieved - [ ] Rule management tooling functional

### Sprint 26: Performance Benchmarking and Optimization

Goal: Comprehensive performance validation

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 26.1 | Benchmark TCAM vs software veto latency | P0 | 8 |
| 26.2 | Benchmark power consumption comparison | P0 | 6 |
| 26.3 | Profile high-frequency decision scenarios | P0 | 8 |
| 26.4 | Optimize critical paths identified | P0 | 12 |
| 26.5 | Document performance characteristics | P0 | 6 |
| 26.6 | Create performance regression tests | P0 | 8 |
| 26.7 | Validate all latency targets met | P0 | 6 |
| 26.8 | Performance tuning guide | P1 | 6 |

Deliverables: - Performance benchmark report - Optimized critical paths - Performance regression test suite - Performance tuning guide

Dependencies: Sprint 25

Acceptance Criteria: - [ ] TCAM veto < 100ns achieved - [ ] Power consumption documented - [ ] All V3 latency targets met - [ ] Performance regression tests pass

## Phase 10: Stakeholder Tooling (Sprints 27-28)

### Sprint 27: Governance Drift Detection

Goal: Tools to detect unintended ethical preference shifts

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 27.1 | Design GovernanceDriftDetector | P0 | 8 |
| 27.2 | Implement baseline decision snapshot | P0 | 6 |
| 27.3 | Implement preference ranking comparison | P0 | 10 |
| 27.4 | Add statistical significance testing | P1 | 8 |
| 27.5 | Implement drift alerting system | P1 | 6 |
| 27.6 | Design FormalVerifier architecture | P0 | 8 |
| 27.7 | Implement ethical invariant specification | P0 | 8 |
| 27.8 | Unit tests for drift detection | P0 | 8 |

Deliverables: - src/erisml/ethics/tooling/drift_detector.py - src/erisml/ethics/tooling/formal_verifier.py - tests/test_drift_detector.py

Dependencies: Sprint 26

Acceptance Criteria: - [ ] Drift detected when preferences shift - [ ] False positive rate < 5% - [ ] Invariants specifiable in DSL - [ ] Alerts generated on significant drift

### Sprint 28: Profile-as-Code and Final Integration

Goal: Declarative profile management and V3 completion

Tasks:

| ID | Task | Priority | Est. Hours |
| --- | --- | --- | --- |
| 28.1 | Enhance Ethical Dialogue CLI for Profile-as-Code | P0 | 10 |
| 28.2 | Implement declarative profile YAML/JSON format | P0 | 8 |
| 28.3 | Add version control integration | P1 | 6 |
| 28.4 | Implement profile diff and merge | P1 | 8 |
| 28.5 | Full V3 integration test suite | P0 | 12 |
| 28.6 | Update all documentation for V3 | P0 | 8 |
| 28.7 | Create V3 migration CLI tool | P0 | 8 |
| 28.8 | Final release preparation | P0 | 8 |

Deliverables: - Enhanced Ethical Dialogue CLI - Profile-as-Code specification - V3 migration tool - Complete V3 documentation - Release package

Dependencies: Sprint 27

Acceptance Criteria: - [ ] Profiles manageable via version control - [ ] CLI supports full Profile-as-Code workflow - [ ] All V3 features documented - [ ] Migration tool validates V2 → V3 upgrade - [ ] V3 ready for production release

## Resource Requirements

### Team Composition

| Role | Count | Sprints | Focus |
| --- | --- | --- | --- |
| Senior Engineer | 2 | 1-28 | Core tensor, architecture |
| ML Engineer | 1 | 11-16, 25-26 | Acceleration, TensorRT, TCAM |
| Security Engineer | 1 | 19-24 | Cryptography, CA, SAIDS |
| Distributed Systems Engineer | 1 | 19-21 | DHT, Blockchain |
| Test Engineer | 1 | 1-28 | Testing, Bond Index |
| Technical Writer | 0.5 | 17-18, 27-28 | Documentation |

### Hardware Requirements

| Hardware | Quantity | Purpose | When Needed |
| --- | --- | --- | --- |
| Development workstations | 3 | Development | Sprint 1+ |
| NVIDIA GPU (RTX 3080+) | 2 | CUDA development | Sprint 12+ |
| Jetson Nano 4GB | 2 | Edge testing | Sprint 13+ |
| Jetson Orin (optional) | 1 | DLA testing | Sprint 13+ |
| CI/CD GPU runners | 1 | Automated testing | Sprint 12+ |

### Software Dependencies

| Dependency | Version | Purpose |
| --- | --- | --- |
| Python | 3.10+ | Runtime |
| NumPy | 1.24+ | Tensor operations |
| SciPy | 1.10+ | Sparse tensors |
| CuPy | 12.0+ | CUDA backend |
| TensorRT | 8.6+ | Jetson optimization |
| JetPack | 5.1+ | Jetson SDK |

## Risk Mitigation

### Technical Risks

| Risk | Mitigation | Contingency |
| --- | --- | --- |
| Rank-6 memory explosion | Low-rank decomposition | Limit to rank-4 |
| Shapley complexity | Monte Carlo approximation | Limit agents to 20 |
| TensorRT compatibility | Version pinning | CPU fallback |
| Jetson SDK changes | JetPack version lock | Document workarounds |

### Schedule Risks

| Risk | Mitigation | Contingency |
| --- | --- | --- |
| Coalition algorithms complex | Start with 2-agent | Defer to V3.1 |
| Hardware unavailable | Cloud Jetson instances | Skip Orin testing |
| Dependencies delayed | Parallel development paths | Adjust scope |

## Success Metrics

### Sprint-Level Metrics

- Sprint velocity: 40-50 story points per sprint

- Bug escape rate: < 5%

- Code review turnaround: < 24 hours

### Release Metrics

- Test coverage: > 90%

- Bond Index: < 0.1 for all EMs

- Performance targets met: 100%

- Documentation complete: 100%

- Zero critical bugs

### Post-Release Metrics

- Migration success rate: > 95%

- Performance improvement: > 3x on GPU

- User satisfaction: > 4.0/5.0

## Appendix: Sprint Calendar

| Sprint | Start Date | End Date | Phase |
| --- | --- | --- | --- |
| 1 | Week 1 | Week 2 | Foundation |
| 2 | Week 3 | Week 4 | Foundation |
| 3 | Week 5 | Week 6 | Foundation |
| 4 | Week 7 | Week 8 | Distributional |
| 5 | Week 9 | Week 10 | Distributional |
| 6 | Week 11 | Week 12 | Distributional |
| 7 | Week 13 | Week 14 | Multi-Agent |
| 8 | Week 15 | Week 16 | Multi-Agent |
| 9 | Week 17 | Week 18 | Multi-Agent |
| 10 | Week 19 | Week 20 | Multi-Agent |
| 11 | Week 21 | Week 22 | Acceleration |
| 12 | Week 23 | Week 24 | Acceleration |
| 13 | Week 25 | Week 26 | Acceleration |
| 14 | Week 27 | Week 28 | Advanced |
| 15 | Week 29 | Week 30 | Advanced |
| 16 | Week 31 | Week 32 | Advanced |
| 17 | Week 33 | Week 34 | Hardening |
| 18 | Week 35 | Week 36 | Hardening |
| 19 | Week 37 | Week 38 | Decentralized Infra |
| 20 | Week 39 | Week 40 | Decentralized Infra |
| 21 | Week 41 | Week 42 | Decentralized Infra |
| 22 | Week 43 | Week 44 | Enforcement |
| 23 | Week 45 | Week 46 | Enforcement |
| 24 | Week 47 | Week 48 | Enforcement |
| 25 | Week 49 | Week 50 | TCAM & Performance |
| 26 | Week 51 | Week 52 | TCAM & Performance |
| 27 | Week 53 | Week 54 | Stakeholder Tooling |
| 28 | Week 55 | Week 56 | Stakeholder Tooling |

Sprint plan maintained by the ErisML Core Team